## Defect logs
Proyect/Task | date | ID | Type | inyected | removed | Counter | description
Window Lifter | 2015-06-26 |  | Documentation | Implementation | Code Review | 1 | Missing proper function comments
Window Lifter | 2015-06-26 |  | Build | Implementation | Code Review | 1 | Outdated headers didn't list changes done to code | Type | Description
Window Lifter | 2015-06-29 |  | System | Implementation | Code Review | 1 | Incorrect system clock configuration
Window Lifter | 2015-06-29 |  | System | Implementation | Code Review | 1 | Magic numbers for led counting | Type | Description
Window Lifter | 2015-06-29 |  | System | Implementation | Code Review | 1 | Direct manipulation of registers | Documentation | comments, messages
[8 empty] | Syntax | spelling, punctuation, typos, instruction formats
[8 empty] | Build, package | change management, library, version control
[8 empty] | Assignment | declaration, duplicate names, scope, limits
[8 empty] | Interface | procedure calls and reference, I/O, user formats
[8 empty] | Checking | error messages, inadequate checks
[8 empty] | Data | structure, content
[8 empty] | Function | logic, pointers, loops, recursion, computation, function defects
[8 empty] | System | configuration, timing, memory
[8 empty] | Environment | design, compile, test, or other support system problems
Note on E3: uids7089: Type of defect Use the next tab to identify the correct classification
Note on F3: uids7089: phase where the issue is Inyected: Requirements Design Implementation
Note on G3: uids7089: phase where the issue is removed: Desing Desing review Code Code Review Module Validation Sw Verification
Note on H3: uids7089: if the same issue is found more that once, increment the conuter

## Types of defects
Type | Description
Documentation | comments, messages
Syntax | spelling, punctuation, typos, instruction formats
Build, package | change management, library, version control
Assignment | declaration, duplicate names, scope, limits
Interface | procedure calls and reference, I/O, user formats
Checking | error messages, inadequate checks
Data | structure, content
Function | logic, pointers, loops, recursion, computation, function defects
System | configuration, timing, memory
Environment | design, compile, test, or other support system problems